## Expenditures & Funding Sources
Capital Improvement Plan 2014 ~2018
Planned Capital Investments 2014-2018 | [7 empty] | Yearly Totals (FS+MTF) | [5 empty] | Funding Sources (5 years total) - Not MTF | [9 empty] | Michigan Transportation Fund (in $1,000's)
| ID No. | Planning Area | Project Limits | Project Type | Justification Score | Construction Year | Total Cost ($1,000s) | FY 2014 | FY 2015 | FY 2016 | FY 2017 | FY 2018 |  | CMAQ | Safety | Bridge (State/Federal) | TEDF-D | TEDF-F | TEDF-A | Other | Local | STU/L | MTF Total | MTF 2014 | MTF 2015 | MTF 2016 | MTF 2017 | MTF 2018 | MTF Total
Asset Mgmt/GIS |  | WCRC | County | GIS/Mapping |  | 2014-2016 | 1000 | 500 | 500 |  |  |  | 1000 | [6 empty] | 900 |  |  | 100 | 50 | 50
Equipment | 8 | WCRC | County | Equipment | 7 | 2014-2018 | 1625 | 325 | 325 | 325 | 325 | 325 | 1625 | [9 empty] | 1625 | 325 | 325 | 325 | 325 | 325 | 1625
Facility and Grounds | 9 | WCRC Property | Countywide | Facility & Grounds | 7 | 2014-2018 | 375 | 75 | 75 | 75 | 75 | 75 | 375 | [9 empty] | 375 | 75 | 75 | 75 | 75 | 75 | 375
Overlay Program | 17 | Countywide | County | Resurface | 8 | 2014-2018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Primary Limestone | 42 | Countywide | County | Resurface | 8 | 2014-2018 | 250 | 50 | 50 | 50 | 50 | 50 | 250 | [9 empty] | 250 | 50 | 50 | 50 | 50 | 50 | 250
Sealcoat Program | 21 | Countywide | County | Resurface | 8 | 2014-2018 | 600 | 300 | 300 | 0 | 0 | 0 | 600 | [9 empty] | 600 | 300 | 300 | 0 | 0 | 0 | 600
0
Grove Road Non-motorized |  | Ypsilanti | Georgina to Rawsonville | Non-motorized | 8 | 2014 | 1142 | 900 | 242 |  |  |  | 1142 | [6 empty] | 763 | 379 |  | 0 | 0 | [5 empty] | tapp 187k non part
Lohr/Textile Greenway II |  | Pittsfield | Lohr to Ann Arbor-Saline | Non-motorized |  | 2014 | 1876 | 1500 | 376 |  |  |  | 1876 | [6 empty] | 1065 | 811 |  | 0 | 0 | [5 empty] | tapp
Border to Border, Phase II | 7 | Countywide | Dexter-Huron Metro-Zeeb | Non-motorized | 8 | 2015 | 90 |  | 90 |  |  |  | 90 | [8 empty] | 90 | 0 |  | 0 |  |  |  | 0
0
Primary Bridge Program | 15 | Countywide | County | Bridge | 8 | 2014-2018 | 450 | 0 | 0 | 150 | 150 | 150 | 450 | [9 empty] | 450 | 0 | 0 | 150 | 150 | 150 | 450 | Used previous CIP numbers
Feldkamp Road Bridge |  | Saline | Over Saline River | Bridge | 9 | 2014 | 950 | 950 |  |  |  |  | 950 |  |  | 790 |  |  |  |  | 80 |  | 80 | 80 | [5 empty] | CE included 95/5
Jackson Road Bridge |  | Lima | Over Mill Creek | Bridge - Preserve Deck |  | 2014 | 440 | 440 |  |  |  |  | 440 |  |  |  | 320 | [5 empty] | 120 | 120 | [5 empty] | sss
McKinley Road Culvert |  | Lima/Sylvan | Over Mill Lake Drain | Bridge |  | 2014 | 200 | 200 |  |  |  |  | 200 | [7 empty] | 100 |  | 100 | 100 | [5 empty] | ??????
Wagner Road Culvert |  | Lodi | Over Unnamed Tributary | Bridge |  | 2014 | 275 |  | 275 |  |  |  | 275 | [6 empty] | 25 |  |  | 250 |  | 250 |  |  |  |  | SSS - 25k hauler $
Austin Road Bridge |  | Saline | Over Saline River | Bridge | 9 | 2015 | 1250 | 100 | 1150 |  |  |  | 1250 |  |  | 950 | [6 empty] | 300 | 100 | 200 |  |  |  |  | SSS
Austin Road Bridge |  | Saline | Over Bauer Drain | Bridge | 9 | 2015 | 1073 | 85 | 988 |  |  |  | 1073 | [8 empty] | 688 | 385 | 85 | 300 |  |  |  |  | CE included 95/5
Dixboro Road Bridge |  | Ann Arbor | Over Huron River | Bridge - Preserve Deck |  | 2015 | 592 |  | 592 |  |  |  | 592.25 |  |  | 489 | [6 empty] | 103.25 |  | 103.25 |  |  |  |  | CE included 95/5
North Territorial Bridge |  | Dexter | Over Huron River | Bridge - Preserve Deck |  | 2015 | 270 |  | 270 |  |  |  | 270.25 |  |  | 223 | [6 empty] | 47.25 |  | 47.25 |  |  |  |  | CE included 95/5
Zeeb Road Bridge |  | Scio | Over Huron River | Bridge - Preserve Deck |  | 2015 | 230 |  | 230 |  |  |  | 230 |  |  | 190 | [6 empty] | 40 |  | 40 |  |  |  |  | CE included 95/5
0
Pavement Preservation STL | 19 | Countywide | County | Resurface | 8 | 2014-2018 | 1737 | 549 | 62 | 369 | 382 | 375 | 1737 | [8 empty] | 1390 | 347 | 110 | 12 | 74 | 76 | 75 | 347 | Used TIP 1/30/13 - 2018 assumed
Pavement Preservation STU | 20 | Countywide | County | Resurface | 8 | 2014-2018 | 2138 | 125 | 201 | 312 | 875 | 625 | 2138 | [8 empty] | 1711 | 427 | 25 | 40 | 62 | 175 | 125 | 427 | Used TIP 1/30/13 - 2018 assumed
Pavement Preservation TEDF-D | 18 | Countywide | County | Resurface | 8 | 2014-2018 | 1037 | 399 | 79 | 186 | 186 | 187 | 1037 |  |  |  | 830 | [5 empty] | 207 | 80 | 16 | 37 | 37 | 37 | 207 | Used TIP 1/30/13 - 2018 assumed
Resurfacing 3R STL |  | Countywide | County | Resurface | 8 | 2014-2018 | 1477 | 475 | 187 | 65 | 375 | 375 | 1477 | [8 empty] | 1182 | 295 | 95 | 37 | 13 | 75 | 75 | 295 | Used TIP 1/30/13 - 2018 assumed
Resurfacing 3R STU |  | Countywide | County | Resurface | 8 | 2014-2018 | 2520 | 81 | 250 | 434 | 880 | 875 | 2520 | [8 empty] | 2017 | 503 | 16 | 50 | 87 | 175 | 175 | 503 | Used TIP 1/30/13 - 2018 assumed
Resurfacing 3R TEDF-D |  | Countywide | County | Resurface | 8 | 2014-2018 | 1203 | 269 | 187 | 191 | 278 | 278 | 1203 |  |  |  | 962 | [5 empty] | 241 | 54 | 37 | 38 | 56 | 56 |  | Used TIP 1/30/13 - 2018 assumed
Pavement Preservation STL-13 | 19 | Countywide | County | Resurface | 8 | 2014 | 695 | 695 |  |  |  |  | 695 | [8 empty] | 556 | 139 | 139 |  |  |  |  | 139 | Used TIP 1/30/13 - 2018 assumed
0
AA-Saline/Ellsworth/Lohr/etc. |  | Pittsfield & Lodi | Various Locations | Signal Upgrade | 7 | 2014 | 360 | 360 |  |  |  |  | 360 | 360 | [8 empty] | 0 | 0 |  |  |  |  | 0 | Verified by Brent & Sheryl
Ann Arbor-Saline Road |  | Pittsfield | Oak Valley to Eisenhower | Resurface | 9 | 2014 | 1486 | 1486 |  |  |  |  | 1485.5 |  |  |  |  | 373 |  |  | 580 | 460 | 72.5 | 72.5 |  |  |  |  | 72.5 | SSS to get back (9/5/13) ADD MDOT & AA EXTRAS
Austin Road |  | Bridgewater | At Eisman | Safety - Correct Superelev | 7 | 2014 | 199 | 199 |  |  |  |  | 198.85 |  | 159 | [7 empty] | 39.85 | 39.85 | [5 empty] | CE ADDED 15% - PE included 50% elibible ($20k)
Austin Road |  | Bridgewater | M-52 to Schneider | Safety - Culverts/Guardrail |  | 2014 | 437 | 437 |  |  |  |  | 437 |  | 342 | [7 empty] | 95 | 95 | [5 empty] | CE ADDED - PE eligible - 50%
Carpenter Road | 39 | Pittsfield | Bemis to Merritt | Safety - Correct Superelev | 7 | 2014 | 436 | 436 |  |  |  |  | 436 |  | 341 | [7 empty] | 95 | 95 |  |  |  |  | 95 | CE ADDED - PE eligible - 50%
Carpenter Road |  | Pittsfield | Packard to Washtenaw | Reconstruction | 9 | 2014 | 2269 | 2210 | 59 |  |  |  | 2269 | [6 empty] | 811 | 100 | 924 | 434 | 332 | 102 |  |  |  | 434 | Included pittsfld sw 200k, assumed CAT A $ (or F?)
Ellsworth Road |  | Ypsilanti | Golfside to Hewitt | Resurface |  | 2014 | 625 | 625 |  |  |  |  | 625 | [8 empty] | 500 | 125 | 125
Jennings Road |  | Webster | N. Territorial to Twp Line | Pave Gravel |  | 2014 | 700 | 700 |  |  |  |  | 700 | [7 empty] | 450 |  | 250 | 250 | [5 empty] | Talk to Roy
Pontiac Trail |  | Salem | At Seven Mile | Safety - Roundabout | 7 | 2014 | 862 | 862 |  |  |  |  | 862 | 750 | [8 empty] | 112 | 112 | [5 empty] | OK for now SSS - LAST YEAR'S INFO - Not Verified or found
Prospect Road |  | Superior | At Cherry Hill | Safety - Hillcut/Flasher |  | 2014 | 265 | 265 |  |  |  |  | 264.5 |  | 207 | [7 empty] | 57.5 | 57.5 | [5 empty] | CE ADDED - PE eligible - 50%
Rawsonville Road |  | Augusta | Talladay to Judd | Resurface | 8 | 2014 | 350 | 350 |  |  |  |  | 350 |  |  |  | 70 |  |  | 175 |  | 105 | 0 | 0 |  |  |  |  | 0 | CE Not Included
Scio Township SAD |  | Scio | Various Roads in Scio | Resurface |  | 2014 | 4000 | 1500 | 1000 | 1000 | 300 | 200 | 4000 | [7 empty] | 4000 |  | 0 | 0 | [5 empty] | Placeholders
Traffic Calming Program |  | Countywide | Various Locations | Safety |  | 2014 | 500 | 100 | 100 | 100 | 100 | 100 | 500 | [7 empty] | 500 |  | 0 | 0 | [5 empty] | Per SSS
0
Hewitt Road |  | Ypsilanti | Michigan Ave to Packard | Resurface | 8 | 2015 | 625 |  | 625 |  |  |  | 625 | [8 empty] | 500 | 125 |  |  | 125 |  |  | 125 | CE Not Included
Huron River Drive/Superior Rd. |  | Ypsilanti | Hewitt to Cornell | Resurface | 8 | 2015 | 500 |  | 500 |  |  |  | 500 | [8 empty] | 400 | 100 |  | 100 |  |  |  |  | CE Not Included
Huron Street |  | Ypsilanti | Huron River Drive to I-94 | Signal Upgrade | 8 | 2015 | 449 |  | 449 |  |  |  | 449 |  | 449 | [7 empty] | 0 |  | 0 |  |  |  |  | CE Not Included
Island Lake Road |  | Dexter | At Wylie | Safety - Hillcut |  | 2015 | 437.5 | 35 | 402.5 |  |  |  | 437.5 |  | 297.5 | [5 empty] | 35 |  | 105 | 17.5 | 87.5 |  |  |  |  | CE ADDED - PE eligible - 50%
Plymouth Road |  | Superior | At Curtis | Safety - Turn Lanes |  | 2015 | 262.5 | 21 | 241.5 |  |  |  | 262.5 |  | 178.5 | [5 empty] | 21 |  | 63 | 10.5 | 52.5 |  |  |  |  | CE ADDED - PE eligible - 50%
Plymouth Road |  | Superior | At Ford | Safety - Turn Lanes/Signal |  | 2015 | 562.5 | 45 | 517.5 |  |  |  | 562.5 |  | 360 | [5 empty] | 67.5 |  | 135 | 22.5 | 112.5 |  |  |  |  | CE ADDED - not FA eligible ($120k)
State Road |  | Pittsfield | Morgan to Ellsworth | Preliminary Engineering | 7 | 2015 | 250 |  | 250 |  |  |  | 250 | [7 empty] | 50 | 200 | 0 |  | 0 |  |  |  | 20 | Assuming match from Pittsfield, no MTF?
Textile Intersections |  | Ypsilanti | Stony Creek and Hitchingham | Safety | 7 | 2015 | 900 |  | 900 |  |  |  | 900 | [6 empty] | 500 |  | 400 | 0 |  | 0 |  |  |  |  | CE Not Included
Willis Road | 3 | Augusta | Hitchingham to Whittaker | Safety | 6 | 2015 | 880 |  | 880 |  |  |  | 880 |  |  |  | 450 |  |  |  | 430 |  | 0 |  | 0 |  |  |  | 0 | CE Not Included
Ann Arbor-Saline Road |  | Lodi | At Textile | Safety - Turn Lane/Signal |  | 2016 | 625 |  |  | 625 |  |  | 625 | [8 empty] | 500 | 125 |  |  | 125 |  |  |  | CE Not Included
Huron Road/Whittaker Road |  | Ypsilanti | Stony Creek to I-94 | Resurface |  | 2016 | 625 |  |  | 625 |  |  | 625 | [8 empty] | 500 | 125 |  |  | 125 |  |  |  | CE Not Included
Prospect Road |  | Superior/Ypsilanti | Holmes to Geddes | Resurface |  | 2016 | 250 |  |  | 250 |  |  | 250 | [8 empty] | 200 | 50 |  |  | 50 |  |  |  | CE Not Included
Rawsonville Road | 35 | Augusta | Oakville-Waltz to Talladay | Resurface | 8 | 2016 | 825 |  |  | 825 |  |  | 825 |  |  |  | 165 |  |  | 412 |  | 248 | 0 |  |  | 0 |  |  | 0 | CE Not Included
Textile Road |  | Lodi | Ann Arbor-Saline to Maple | Resurface |  | 2016 | 500 |  |  | 500 |  |  | 500 | [8 empty] | 400 | 100 |  |  | 100 |  |  |  | CE Not Included
Carpenter Road |  | York/Pittsfield | Judd to Textile | Resurface |  | 2017 | 625 |  |  |  | 625 |  | 625 | [8 empty] | 500 | 125 |  |  |  | 125 |  |  | CE Not Included
Whittaker Road |  | Ypsilanti | At Merritt | Safety - Roundabout |  | 2017 | 875 |  |  |  | 875 |  | 875 | [8 empty] | 700 | 175 |  |  |  | 175 |  |  | CE Not Included
Seven Mile Road | 26 | Northfield | Main to Donna Lane | New Construction | 6 | 2018 | 1803 |  |  |  | 100 | 1703 | 1803 | [7 empty] | 1015 | 628 | 160 |  |  |  |  | 160 | 157 | CE Not Included
0
2013-11-11 | [5 empty] | Totals | 46978.5 | 17149 | 11853.5 | 6082 | 5576 | 5318 | 46977.85 | 1110 | 2334 | 2642 | 2797 | 373 | 0 | 4651 | 8618.5 | 14799 | 9653.35 | 3033.35 | 2387 | 1436 | 1494 | 1303 | 6121.5 | 46977.85
6121.5
Washtenaw County Road Commission
[11 empty] | 45978.5 | [10 empty] | 37324.5 |  | 9653.35
46977.85

## MTF By Year
DRAFT
2008 - 2012 Capital Improvement Program - MTF Obligations | [7 empty] | MTF By Year ($1,000s) | [5 empty] | MTF TOTAL
Project Name | ID No. | Planning Area | Project Limits | Project Type | Justification Score | Construction Year | Total Cost ($1,000s) | FY 2008 | FY 2009 | FY 2009II | FY 2010 | FY 2011 | FY 2012
Milan-Oakville | 1 | Augusta | Milan City to 0.5 Mile East of Gooding | Reconstruct | 9 | 2008 | #REF! | MTF By Year ($1,000s) FY 2009: 0; MTF By Year ($1,000s) FY 2009II: 100 | 100
Rawsonville | 2 | Augusta | Oakville-Waltz to Wear | Resurface | 9 | 2008 | #REF! | MTF By Year ($1,000s) FY 2009: 20; MTF By Year ($1,000s) FY 2009II: 0 | 20
Willis | 3 | Augusta | Lincoln HS @ Bellemeade | Widen | 8 | 2009 | #REF! | [6 empty] | 0
Warren @ Dixboro Culvert | 4 | Ann Arbor | Warren @ Dixboro | Bridge | 7 | 2009 | #REF! | MTF By Year ($1,000s) FY 2009: 130; MTF By Year ($1,000s) FY 2009II: 0; MTF By Year ($1,000s) FY 2010: 130 | 260
Joy @ Dixboro Culvert | 5 | Ann Arbor | Joy @ Dixboro | Bridge | 7 | 2009 | #REF! | MTF By Year ($1,000s) FY 2009: 100; MTF By Year ($1,000s) FY 2009II: 0; MTF By Year ($1,000s) FY 2010: 100 | 200
Warren Road Culvert | 6 | Ann Arbor | Warren West of Dixboro | Bridge | 7 | 2009 | #REF! | MTF By Year ($1,000s) FY 2009: 160; MTF By Year ($1,000s) FY 2009II: 0; MTF By Year ($1,000s) FY 2010: 160 | 320
Border to Border | 7 | Countywide | County | Non-motorized | 8 | 2009 | #REF! | [6 empty] | 0
Bridge & Culvert Preservation | 42 | Countywide | County | Bridge | 8 | 2008-2012 | #REF! | 100 | 100 | 100 | 100 | 100 | 100 | 600
Equipment | 8 | WCRC | County | Equipment | 7 | 2008-2012 | 1625 | 400 | 400 | 400 | 400 | 400 | 400 | 2400
General Facility and Grounds | 9 | WCRC | County | Facility | 7 | 2008-2012 | 375 | MTF By Year ($1,000s) FY 2010: 150; MTF By Year ($1,000s) FY 2011: 150; MTF By Year ($1,000s) FY 2012: 150 | 450
Zeeb Road Facility and Grounds | 10 | WCRC (Scio) | Zeeb Road (Scio) Facility | Facility | 7 | 2008-2012 | #REF! | MTF By Year ($1,000s) FY 2008: 375; MTF By Year ($1,000s) FY 2012: 207 | 582
Chelsea Facility and Grounds | 11 | WCRC (Chelsea) | Chelsea Facility | Facility | 9 | 2008-2012 | #REF! | MTF By Year ($1,000s) FY 2008: 419 | 419
Manchester Facility and Grounds | 12 | WCRC (Manchester) | Manchester Village Facility | Facility | 9 | 2008-2012 | #REF! | 15 | 295 | 0 | 295 |  |  | 605
Salem Facility and Grounds | 13 | WCRC (Salem) | Salem Facility | Facility | 7 | 2008-2012 | #REF! | MTF By Year ($1,000s) FY 2008: 0; MTF By Year ($1,000s) FY 2009: 380; MTF By Year ($1,000s) FY 2009II: 0 | 380
Intersection Improvements | 14 | Countywide | County | Intersection/Safety | 8 | 2008-2012 | #REF! | MTF By Year ($1,000s) FY 2011: 250; MTF By Year ($1,000s) FY 2012: 250 | 500
Local Bridge Program | 15 | Countywide | County | Bridge | 8 | 2008-2012 | #REF! | MTF By Year ($1,000s) FY 2011: 250; MTF By Year ($1,000s) FY 2012: 250 | 500
Non-Motorized | 16 | Countywide | County | Non-motorized | 7 | 2010 | #REF! | [6 empty] | 0
Overlay Program | 17 | Countywide | County | Resurface | 8 | 2008-2012 | 0 | 150 | 150 | 300 | 150 | 150 | 150 | 1050
Pavement Preservation Cat. D | 18 | Countywide | County | Resurface | 8 | 2008-2012 | #REF! |  |  | 10 | 50 | 50 | 50 | 160
Pavement Preservation STP-R | 19 | Countywide | County | Resurface | 8 | 2008-2012 | #REF! |  |  | 90 | 50 | 50 | 50 | 240
Pavement Preservation STP-U | 20 | Countywide | County | Resurface | 8 | 2012 | #REF! | MTF By Year ($1,000s) FY 2009II: 90; MTF By Year ($1,000s) FY 2012: 500 | 590
Sealcoat Program | 21 | Countywide | County | Resurface | 8 | 2008-2012 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 1500
Dexter-Pinckney Bridge | 22 | Dexter | Over Portage Canal | Bridge | 9 | 2009 | #REF! | 100 | 280 | 50 | 100 |  |  | 530
Liberty Bridge | 23 | Lima | Over Haas Drain | Bridge | 8 | 2008 | #REF! | MTF By Year ($1,000s) FY 2008: 250 | 250
Schleweis Road Bridge | 24 | Manchester | Over Iron Creek | Bridge | 9 | 2008 | #REF! | MTF By Year ($1,000s) FY 2008: 0; MTF By Year ($1,000s) FY 2010: 200 | 200
North Territorial | 25 | Northfield | Nollar to Whitmore Lake | Reconstruct | 10 | 2009 | #REF! | MTF By Year ($1,000s) FY 2008: 0; MTF By Year ($1,000s) FY 2009: 0; MTF By Year ($1,000s) FY 2009II: 0 | 0
Seven Mile | 26 | Northfield | Main to Donna Lake | Construct | 7 | 2011 | #REF! | 20 | 0 | 0 | 0 | 0 |  | 20
Carpenter | 27 | Pittsfield | Textile to I-94 | Widen | 10 | 2008 | #REF! | MTF By Year ($1,000s) FY 2008: 225 | 225
Carpenter |  | Pittsfield | Washtenaw to Packard |  |  |  | #REF!
Munger at Textile | 28 | Pittsfield | Munger at Textile | Intersection/Safety | 8 | 2008 | #REF! | MTF By Year ($1,000s) FY 2008: 15 | 15
Main Street Phase II | 46 | Scio | Norfolk Southern RR to Mill Creek | Bridge | 9 | 2010 | #REF!
East Delhi | 29 | Scio | Over Huron River | Bridge | 7 | 2009 | #REF! | MTF By Year ($1,000s) FY 2008: 120; MTF By Year ($1,000s) FY 2009: 45; MTF By Year ($1,000s) FY 2009II: 45 | 210
Jackson | 30 | Scio | Honey Creek to Dino Drive | Widen | 10 | 2008 | #REF! | [6 empty] | 0
Main Street | 31 | Scio | Over Mill Creek | Bridge | 11 | 2008 | #REF! | MTF By Year ($1,000s) FY 2008: 200 | 200
Geddes Non-motorized | 32 | Superior | County | Non-motorized | 8 | 2010 | #REF! | MTF By Year ($1,000s) FY 2010: 40 | 40
Geddes/Leforge | 45 | Superior | At Leforge | Intersection | 10 | 2008 | #REF! | [6 empty] | 0
Plymouth Bridge | 33 | Superior | Over Fleming Creek | Bridge | 8 | 2009 | #REF! | MTF By Year ($1,000s) FY 2008: 40; MTF By Year ($1,000s) FY 2009: 120; MTF By Year ($1,000s) FY 2009II: 50 | 210
Superior @ Geddes | 34 | Superior | At Geddes | Intersection/Safety | 8 | 2008 | #REF! | MTF By Year ($1,000s) FY 2008: 250 | 250
Bemis/Platt/Willis | 44 | York | Bemis/Platt/Willis | Resurface | 10 | 2008 | #REF! | [6 empty] | 0
Ford Boulevard II | 35 | Ypsilanti | US-12 to Ecorse | Resurface | 8 | 2010 | #REF! | MTF By Year ($1,000s) FY 2009: 30; MTF By Year ($1,000s) FY 2009II: 30; MTF By Year ($1,000s) FY 2010: 135 | 195
Golfside | 36 | Ypsilanti | Packard to Clark | Resurface | 7 | 2011 | #REF! | MTF By Year ($1,000s) FY 2010: 20; MTF By Year ($1,000s) FY 2011: 130 | 150
Hewitt | 37 | Ypsilanti | Packard to Clark | Resurface | 8 | 2009 | #REF! | MTF By Year ($1,000s) FY 2008: 40; MTF By Year ($1,000s) FY 2009: 130; MTF By Year ($1,000s) FY 2009II: 130 | 300
Holmes II | 38 | Ypsilanti | Rue Deauville to Spencer | Reconstruct | 9 | 2008 | #REF! | MTF By Year ($1,000s) FY 2008: 30 | 30
Holmes III | 39 | Ypsilanti | Spencer to Michigan | Reconstruct | 9 | 2010 | #REF! | MTF By Year ($1,000s) FY 2008: 50; MTF By Year ($1,000s) FY 2009: 100; MTF By Year ($1,000s) FY 2009II: 100 | 250
Mansfield St |  | Ypsilanti | Westmoreland to Congress | Reconstruct |  |  | #REF!
Whittaker | 40 | Ypsilanti | At Stony Creek | Intersection/Safety | 11 | 2009 | #REF! | [6 empty] | 0
Whittaker | 41 | Ypsilanti | At Merritt | Intersection/Safety | 8 | 2011 | #REF! |  | 50 | 50 | 100 | 350 |  | 550
Signal Interconnect | 43 | Ypsi/AA/Pitt/Sup | See Below | Intersection/Safety | 9 | 2008 | #REF! | MTF By Year ($1,000s) FY 2008: 60 | 60
[6 empty] | Totals | #REF! | 3109 | 2740 | 1795 | 2430 | 2130 | 2357 | 14561
The 2008-2012 CIP includes $5.5 million in non-yet-identified projects represented in the Countywide funding category. This represents approximately 10% of the total estimated capital investment capacity.
The Multi-Road CMAQ project has the following limits: Dixboro from Geddes to Huron River Drive and continuing on Huron River Drive to Golfside; Golfside to Washtenaw Avenue; and Clark from Hogback to Huron River Drive and Huron River Drive to Leforge.
Although the Seven Mile Road construction has been deleted from the CIP, the WCRC is still committed to completing the Environmental Assessment for that project in 2008.

## Sheet3
Bridge | 130
Bridge | 100
Bridge | 160
Bridge | 500
Bridge | 2500
Bridge | 1710
Bridge | 250
Bridge | 200
Bridge | 1305
Bridge | 2040
Bridge | 710 | 9605 | 11 Bridges
Construct | 2050 | 2050 | 1 Construct
Equipment | 2000 | 2000 | 1 Equipment
Facility | 750
Facility | 955
Facility | 525
Facility | 415
Facility | 400 | 3045 | 5 Facility
Intersection/Roundabout | 1580
Intersection/Roundabout | 1325
Intersection/Roundabout | 1300 | 4205 | 3 Intersection/Roundabout
Mill & Resurface | 380
Mill & Resurface | 455
Mill & Resurface | 455
Mill & Resurface | 455 | 1745 | 4 Mill & Resurface
Non-motorized | 294
Non-motorized | 160
Non-motorized | 440 | 894 | 3 Non-motorized
Reconstruct | 2695
Reconstruct | 1170
Reconstruct | 4490
Reconstruct | 3200 | 11555 | 4 Reconstruct
Resurface | 750
Resurface | 750
Resurface | 750
Resurface | 500
Resurface | 1250 | 4000 | 5 Resurface
Safety | 360 | 360 | 1 Safety
Signal/Intersection | 500
Signal/Intersection | 105 | 605 | 2 Signal/Intersection
Widen | 17600 | 17600 | 1 Widen
Widen/Resurface | 910 | 910 | 1 Widen/Resurface
Widen; Mill & Reconstruct | 1885 | 1885 | 1 Widen; Mill & Resurface
60459